## Sheet1
No. | Product Deliverables | Task | Mai Văn Tân | Bùi Việt Phong | Hồ Đắc Nghĩa | Trần Lê Tuấn | Unit | Size
1 | Report1 - Introduction | Project Information | O
|  | Introduction | O
|  | Current System | O
|  | Proposed Solution | O
|  | Functional Requirement | O
|  | Roles and Responsibility | O
2 | Report2- Software Project Management Plan | Problem Definition | O
|  | Project organization | O
|  | Project management plan | O
|  | Coding Convention | O
3 | Report 3- Software Requirement Specification | User Requirement Specification |  | O
System Requirement Specification
|  | External Interface Requirements |  | O
Functional Requirement
Admin Requirement
|  | Manage account | O
|  | Configure system | O
Staff Requirement
|  | Add traffic sign | O
|  | View report |  | O
|  | System Requirement | O
User Requirement
|  | Add favorite |  | O
|  | Report |  | O
Guest Requirement
|  | Search traffic sign | O
…
Non-functional Requirement
|  | Reliability | O
|  | Availability |  | O
|  | Sercurity |  | O
|  | Maintainability |  | O
|  | Performance | O
|  | Conceptual Diagram | O
|  | Data Dictionary | O
| Report 4- Software Design Description | Design Overview | O
|  | System Architectural Design | O
|  | Component Diagram | O
|  | Class diagram | O
Class specification (states, behaviors)
|  | TrafficInfo |  | O
|  | Account |  | O
|  | Category |  | O
|  | TrainImage |  | O
|  | Favorite |  | O
|  | Result |  | O
|  | Report |  | O
Sequence Diagram
|  | Add Traffic Sign | O
|  | Add Train Image | O
|  | Import Data From File | O
|  | Search Auto |  | O
|  | Search Manual |  | O
Database Design
|  | Entity Relationship Diagram | O
|  | Data Dictionary | O
Algorithms
|  | Tracffic Detect | O
|  | Tracffic Recognize | O
|  | Sync favorite |  | O
5 | Report 5 - Software Implementation and Test Document | Setup Environtment
|  | Web | O
|  | Mobile Client |  | O
Traffic Detect and Recognize
|  | Traffic Detect | O |  |  |  |  | 4
|  | Traffic Recognize | O |  |  |  |  | 4
Web Serivce
|  | Register | O |  |  |  |  | 1
|  | Login | O |  |  |  |  | 1
|  | Forgot password | O |  |  |  |  | 1
|  | Change password | O |  |  |  |  | 1
Manage account
|  | Active/Deactivated | O |  |  |  |  | 1
|  | Set/Unset staff | O |  |  |  |  | 1
Manage traffic sign
|  | Add/Edit/Delete | O |  |  |  |  | 1
Manage report
|  | Fix wrong information | O |  |  |  |  | 1
|  | Fix wrong recognition | O |  |  |  |  | 1
|  | Server configure | O |  |  |  |  | 1
Statistic service
|  | Statistic register | O |  |  |  |  | 1
|  | Statistic search | O |  |  |  |  | 1
Search Service
|  | Search manual | O |  |  |  |  | 1
|  | Search auto | O |  |  |  |  | 2
|  | Import/Export Data | O |  |  |  |  | 2
Website Client
|  | Register | O |  |  |  |  | 1
|  | Login/Logout/Forgot password | O |  |  |  |  | 1
Manage account
|  | Active/Deactivated | O |  |  |  |  | 1
|  | Set/Unset staff | O |  |  |  |  | 1
Manage traffic sign
|  | Add/Edit/Delete | O |  |  |  |  | 2
Manage report
|  | Fix wrong information | O |  |  |  |  | 1
|  | Fix wrong recognition | O |  |  |  |  | 2
|  | Server configure | O |  |  |  |  | 1
Statistic service
|  | Statistic register | O |  |  |  |  | 1
|  | Statistic search | O |  |  |  |  | 1
|  | Import/Export Data | O |  |  |  |  | 1
|  | Search Manual |  | O |  |  |  | 1
|  | Search Auto | O |  |  |  |  | 2
Manage favorite
|  | Add/Remove |  | O |  |  |  | 1
|  | View |  | O |  |  |  | 1
|  | Manage history |  | O
|  | View/Delete | [5 empty] | 1
Send report
|  | Wrong traffic information |  | O |  |  |  | 1
|  | Wrong recongniton |  | O |  |  |  | 1
Mobile Client
|  | Register |  | O |  |  |  | 1
|  | Login |  | O |  |  |  | 1
Search Manual
|  | Search by keyword |  | O |  |  |  | 1
|  | Search by category |  | O |  |  |  | 1
Search Auto
|  | Search by upload image |  | O |  |  |  | 1
|  | Search by take picture |  | O |  |  |  | 1
|  | Auto detect traffic sign |  | O |  |  |  | 2
|  | Search when no internet connection |  | O |  |  |  | 2
|  | Auto capture image |  | O |  |  |  | 2
Manage favorite
|  | Add/Delete |  | O |  |  |  | 1
|  | Sync favorite |  | O |  |  |  | 3
Manage history
|  | View/Delete |  | O |  |  |  | 1
|  | Sync traffc sign data |  | O |  |  |  | 2
Send report
|  | Wrong traffic information |  | O |  |  |  | 1
|  | Wrong recongniton |  | O |  |  |  | 1
|  | Mobile app setting |  | O |  |  |  | 1
|  | DB diagrams | O
Write Test case
|  | Manage user | O
|  | Manage traffic sign | O
|  | Auto search |  | O
|  | Manual search |  | O
Perform Testing
|  | Manage user | O
|  | Manage traffic sign | O
|  | Auto search |  | O
|  | Manual search |  | O
6 | Report 6 - Software User's Manual | Installation Guide
|  | Web | O
|  | Mobile Client |  | O
Admin guide
|  | Manage account | O
|  | Config System | O
Staff guide
|  | Manage traffic sign | O
|  | Mange account | O
|  | Manage report | O
User guide - Mobile
|  | Register |  | O
|  | Login |  | O
|  | Auto search |  | O
|  | Manual search |  | O
|  | View History |  | O
|  | Report wrong traffic sign |  | O
User guide - Web
|  | Auto search |  | O
|  | Manual search |  | O
|  | View History |  | O
|  | Report wrong traffic sign |  | O
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C13: phuong: Use bold format for tasks which have sub-tasks
Note on C14: phuong: Use Indent for sub-tasks