## Sheet1
No. | Product Deliverables | Task | Mai Văn Tân | Bùi Việt Phong | Hồ Đắc Nghĩa | Trần Lê Tuấn | Unit | Size
1 | Report1 - Introduction | Project Information | O
|  | Introduction | O
|  | Current System | O
|  | Proposed Solution | O
|  | Functional Requirement | O
|  | Roles and Responsibility | O
2 | Report2- Software Project Management Plan | Problem Definition | O
|  | Project organization | O
|  | Project management plan | O
|  | Coding Convention | O
3 | Report 3- Software Requirement Specification | User Requirement Specification |  | O
|  | System Requirement Specification |  | O
|  | External Interface Requirements |  | O
|  | Functional Requirement |  | O
|  | Admin Requirement |  | O
|  | Staff Requirement |  | O
|  | System Requirement |  | O
|  | User Requirement |  | O
|  | Guest Requirement |  | O
|  | Non-functional Requirement |  | O
|  | Reliability |  | O
|  | Availability |  | O
|  | Sercurity |  | O
|  | Performance |  | O
|  | Conceptual Diagram | O
|  | Data Dictionary | O
| Report 4- Software Design Description | Design Overview | O
|  | System Architectural Design | O
|  | Component Diagram | O
|  | Class diagram | O
Detailed Description of Components
|  | Sequence Diagram | O
|  | Add Traffic Sign | O
|  | Add Train Image | O
|  | Import Data From File | O
|  | Search Auto | O
|  | Search Manual | O
Database Design
|  | Entity Relationship Diagram | O
|  | Data Dictionary | O
Algorithms
|  | Tracffic Detect | O
|  | Tracffic Recognize | O
|  | Sync Data |  | O
5 | Report 5 - Software Implementation and Test Document | Setup Environtment | O
|  | Web | O
|  | Mobile Client |  | O
Traffic Detect and Recognize
|  | Traffic Detect | O |  |  |  |  | 4
|  | Traffice Recognize | O |  |  |  |  | 4
Web Serivce
|  | Register | O |  |  |  |  | 1
|  | Login | O |  |  |  |  | 1
|  | Forgot password | O |  |  |  |  | 1
|  | Change password | O |  |  |  |  | 1
|  | Manage account | O |  |  |  |  | 2
|  | Manage traffic sign | O |  |  |  |  | 3
|  | Server configure | O |  |  |  |  | 1
|  | Statistic service | O |  |  |  |  | 1
|  | Search Service | O |  |  |  |  | 3
|  | Import/Export Data | O |  |  |  |  | 2
Website Client
|  | Register | O |  |  |  |  | 1
|  | Login/Logout/Forgot password | O |  |  |  |  | 1
|  | Manage account | O |  |  |  |  | 2
|  | Manage traffic sign | O |  |  |  |  | 3
|  | Manage report | O |  |  |  |  | 2
|  | Server configure | O |  |  |  |  | 1
|  | Import/Export Data | O |  |  |  |  | 2
|  | Search Manual |  | O |  |  |  | 3
|  | Search Auto | O |  |  |  |  | 3
|  | Manage favorite |  | O |  |  |  | 2
|  | Manage history |  | O |  |  |  | 2
|  | Send report |  | O |  |  |  | 2
Mobile Client
|  | Register |  | O |  |  |  | 1
|  | Login |  | O |  |  |  | 1
|  | Search Manual |  | O |  |  |  | 3
|  | Search Auto |  | O |  |  |  | 4
|  | Manage favorite |  | O |  |  |  | 2
|  | Manage history |  | O |  |  |  | 2
|  | Sync Data |  | O |  |  |  | 4
|  | DB diagrams | O
Write Test case
|  | Manage user | O
|  | Manage traffic sign | O
|  | Auto search |  | O
|  | Manual search |  | O
|  | Perform Testing | O
|  | Manage user | O
|  | Manage traffic sign |  | O
|  | Auto search |  | O
Manual search
6 | Report 6 - Software User's Manual | Installation Guide
|  | Web | O
|  | Mobile Client |  | O
Admin guide
|  | Manage account | O
|  | Config System | O
Staff guide
|  | Manage traffic sign | O
|  | Mange account | O
|  | Manage report | O
User guide - Mobile
|  | Register |  | O
|  | Login |  | O
|  | Auto search |  | O
|  | Manual search |  | O
|  | View History |  | O
|  | Report wrong traffic sign |  | O
User guide - Web
|  | Auto search |  | O
|  | Manual search |  | O
|  | View History |  | O
|  | Report wrong traffic sign |  | O
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C13: phuong: Use bold format for tasks which have sub-tasks
Note on C14: phuong: Use Indent for sub-tasks